Customer Service Modernization Proposal

Executive proposal for a controlled eight-center pilot

| Proposal owner | Customer Experience Division |
| --- | --- |
| Decision requested | Approve a 12-week pilot across eight service centers |
| Estimated budget | THB 8.4 million |
| Proposed start | 1 October 2026 |
| Document status | Workshop sample - fictional data |

# Executive Summary

This proposal requests approval for a 12-week pilot across eight customer service centers. The pilot combines digital queue management, guided request checks, and a staff dashboard while keeping final customer and case decisions with authorized employees.

Synthetic baseline observations show an average service wait of 18 minutes, a first-contact resolution rate of 62%, and a repeat-contact rate of 14%. These values are fictional workshop data and do not represent the performance of any real organization.

# Business Need

- Customers receive inconsistent guidance about the information required for service requests.

- Employees switch between multiple screens to check queue status, request completeness, and case ownership.

- Managers receive delayed operational data and cannot isolate the causes of repeat contacts.

# Pilot Scope

The pilot covers eight service centers with different traffic profiles.

- Digital queue check-in and estimated waiting-time display.

- Guided request checklist for common service cases.

- Staff dashboard showing queue volume, case age, and ownership.

- Weekly review of service metrics, employee feedback, and customer comments.

Out of scope: automated case approvals, changes to core service-system logic, replacement of the customer relationship platform, and organization-wide rollout.

# Expected Benefits and Measures

- Reduce average service wait from 18 minutes to 14 minutes or less.

- Increase first-contact resolution from 62% to at least 70%.

- Reduce repeat contacts from 14% to 10% or less.

- Achieve at least 80% weekly active use among participating employees.

# Delivery Plan

- Weeks 1-3: discovery, center selection, data review, and security review.

- Weeks 4-6: configuration, integration testing, and checklist review.

- Weeks 7-9: employee testing, training, and readiness checks.

- Weeks 10-12: live pilot, daily issue review, and final evaluation.

# Cost and Assumptions

The THB 8.4 million estimate includes software configuration, integration support, training, pilot communications, and contingency. It assumes existing service-center devices can be reused and that internal teams can support data mapping and security review.

The estimate excludes organization-wide licenses, major network upgrades, and long-term support after the pilot. Detailed vendor quotations are not attached.

# Key Risks and Controls

- Customer data could appear in the wrong dashboard view; role-based access and privacy review are required.

- Network stability is described as adequate, but no center-by-center baseline evidence is attached.

- Employee adoption may vary by center; local champions and weekly feedback are proposed as controls.

- Integration effort may exceed the estimate; a technical discovery checkpoint is required before configuration.

# Dependencies and Missing Information

- Named accountable owner for the pilot has not been confirmed.

- Privacy and security review dates are not yet scheduled.

- Service-center network evidence is not attached.

- Detailed vendor quotations and post-pilot support costs are missing.

- The method for measuring first-contact resolution needs final agreement.

# Decision Requested

Approve the 12-week pilot and the THB 8.4 million budget, subject to confirmation of the accountable owner, privacy review schedule, network evidence, and detailed vendor quotations before configuration begins.